## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | Letterboxd
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2026-01-02 | Adnan | 1. Open preffered web browser 2. Go to https://letterboxd.com/brazyben/list/ 3. Choose any list 4. Scroll down to the comment section 5. Click "Enable Notifications in the Settings" 6. It will prompt you to log in 7. When you enter you credentials you get stuck in an infinite loop EXPECTED RESULT: The website leads you back to the list with a pop up dialog of confirmation ACTUAL RESULT: User gets stuck in an infinite loop VIDEO: - https://edufit-my.sharepoint.com/:v:/g/personal/marko_dogan_edu_fit_ba/IQAPfxL3swn9RJva6NXC_yt1AfP24o2XTa__sb1RVZRRqYc?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=hVIvFN | Executing/Controlling | Post-Deployment | Low | Letterboxd Development Team | 2026-01-01 | 2 hours | New | Not resolved – defect logged |  |  | Session state is not preserved after authentication. The intended action is lost during the login redirect flow. | New
2 | 2026-01-05 | Marko | 1. Open preffered web browser 2. Go to https://www.letterboxd.com/settings 3. Enter valid credentials 4. Click Sign In 5. Click the Profile tab of the Settings page 6. Click into the Website field 7. Paste the provided InvalidURL into the field 8. Click Save Changes EXPECTED RESULT: The Website field border changes color to red and error message shown below the field ACTUAL RESULT: Changes are saved with the invalid URL VIDEO: - https://edufit-my.sharepoint.com/:v:/g/personal/marko_dogan_edu_fit_ba/IQCJas75YvlvSqafTadRcorFASMbXpJHw8jLBGBsNIRNfEE?e=SyXVAd | Executing/Controlling | Post-Deployment | Low | Letterboxd Development Team | 2026-01-05 | <1hr | New | Not resolved – defect logged |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 2026-01-05 | Marko | 1. Open preffered web browser 2. Go to https://www.letterboxd.com/settings 3. Enter valid credentials 4. Click Sign In 5. Click the Profile tab of the Settings page 6. Click into the Website field 7. Paste the provided InvalidURL into the field 8. Click Save Changes 9. Navigate to your Profile page 10. Click the website link EXPECTED RESULT: The system warns you about the malformed URL and/or that the redirect will lead you out of the current app. ACTUAL RESULT: The system redirects the user to non-existent sites, without any warning about it. VIDEO: - https://edufit-my.sharepoint.com/:v:/g/personal/marko_dogan_edu_fit_ba/IQASpaC29ng3TJl_8nJ7ejBCAcyJQjOHa3U-zHHGq8RdY58?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=yzyttJ | Executing/Controlling | Post-Deployment | Low | Letterboxd Development Team | 2026-01-05 | 1hr | New | Not resolved – defect logged |  |  |  | In Progress | Medium | Initiating | Concept
4 | 2026-01-05 | Marko | 1. Open preffered web browser 2. Go to https://www.letterboxd.com/settings 3. Enter valid credentials 4. Click Sign In 5. Click the Profile tab of the Settings page 6. Click & Hold on the bottom right edge of the Bio field 7. Resize the field to the width of the screen 8. Let go of the mouse click EXPECTED RESULT: The field snaps back to defined maximum width to avoid UI problems. ACTUAL RESULT: The field stays resized to the screen width overlapping the favorite films section of the page VIDEO: - https://edufit-my.sharepoint.com/:v:/g/personal/marko_dogan_edu_fit_ba/IQDei6MM00KiRK3b2L0elkSvAd7Mr5nvRK2Cv3W1_mujRh0?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=zrtx65 | Executing/Controlling | Post-Deployment | Low | Letterboxd Development Team | 2026-01-05 | <1hr | New | Not resolved – defect logged |  |  |  | Completed | Low | Planning | Requirements
5 | 2026-01-05 | Marko | 1. Open preffered web browser 2. Go to https://www.letterboxd.com/settings 3. Enter valid credentials 4. Click Sign In 5. Click the Profile tab of the Settings page 6. Click into the Location field 7. Paste the provided InvalidLocation into the field 8. Click Save Changes EXPECTED RESULT: The Location field border changes color to red and error message shown below the field ACTUAL RESULT: The changes are saved with an invalid location VIDEO: - https://edufit-my.sharepoint.com/:v:/g/personal/marko_dogan_edu_fit_ba/IQAIlzQwgtAATbXTCDQzhWUxATZ-EwA9F9-DA6fZgNP42LE?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=217f1s | Executing/Controlling | Post-Deployment | Low | Letterboxd Development Team | 2026-01-05 | <1hr | New | Not resolved – defect logged | [5 empty] | Executing/Controlling | Design
6 | 2026-01-05 | Marko | 1. Open preffered web browser 2. Go to https://www.letterboxd.com/settings 3. Enter valid credentials 4. Click Sign In 5. Click the Avatar tab of the Settings page 6. Click the Select New Avatar button 7. Select provided test Image 8. Click the Open button in the dialog 9. Read the toast message EXPECTED RESULT: The toast informs us that the image is too small and specifies the minimum required size ACTUAL RESULT: The toast informs us only that the picture is too small but it doesn't provide the minimum required size VIDEO: - https://edufit-my.sharepoint.com/:v:/g/personal/marko_dogan_edu_fit_ba/IQASbHRvOTnBSqU1M-iLvg1zATt04U4bZaGdFSTQ1gP9J4k?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=sKRxbR | Executing/Controlling | Post-Deployment | Low | Letterboxd Development Team | 2026-01-05 | 2hr | New | Not resolved – defect logged | [5 empty] | Closing | Development
7 | 2026-01-05 | Marko | 1. Open preffered web browser 2. Go to https://www.letterboxd.com/settings 3. Enter valid credentials 4. Click Sign In 5. Click the Avatar tab of the Settings page 6. Click the Select New Avatar button 7. Select provided test Image 8. Click the Open button in the dialog 9. Read the toast message 10. Again click the Select New Avatar button 11. Select provided test Image again 12. Click the Open button in the dialog again 13. Read the toast message EXPECTED RESULT: The toast informs us that the upload failed with the reason for the failure ACTUAL RESULT: No toast is displayed to inform the user that the upload has failed VIDEO: - https://edufit-my.sharepoint.com/:v:/g/personal/marko_dogan_edu_fit_ba/IQBTDsy9N0DAQ7UobVvLwdCzAe9iLcfuC6-IgULVEET78J0?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=IO8YUa | Executing/Controlling | Post-Deployment | Medium | Letterboxd Development Team | 2026-01-05 | 3hr | New | Not resolved – defect logged | [6 empty] | Testing
8 | 2026-01-05 | Marko | 1. Open preffered web browser 2. Go to https://www.letterboxd.com/settings 3. Enter valid credentials 4. Click Sign In 5. Click the Avatar tab of the Settings page 6. Verify the maximum picture upload size 7. Verify that the provided test image is larger then the system should allow 8. Click the Select New Avatar button 9. Select provided test Image 10. Click the Open button in the dialog 11. Read the toast message EXPECTED RESULT: The toast informs us that the image is too large and specifies the maximum required size ACTUAL RESULT: The picture upload succeds, allowing the user to upload pictures larger than the specified maximum size VIDEO: - https://edufit-my.sharepoint.com/:v:/g/personal/marko_dogan_edu_fit_ba/IQCr9gA8cdeoTYr_qlVmzsU8Ac0wQY0NprbYow-VnRZLuqc?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=Si34Vn | Executing/Controlling | Post-Deployment | High | Letterboxd Development Team | 2026-01-05 | 3hr | New | Not resolved – defect logged | [6 empty] | Documentation and Training
9 | 2026-01-05 | Marko | 1. Open preffered web browser 2. Prepare device with an authenticator app 3. Go to https://www.letterboxd.com/settings 4. Enter valid credentials 5. Click Sign In 6. Click the Auth tab of the Settings page 7. Click the Enable button under the Enable 2FA header 8. Scan the QR code with your chosen authenticator app 9. Click into the Current password field 10. Paste the Current Password into the field 11. Click into the Two-factor auth code field 12. Enter the 2FA obtained from the app into the field 13. Click Enable EXPECTED RESULT: A pop-up displays the required account recovery codes needed to not lose your account if you lose your auth device ACTUAL RESULT: The codes are not displayed, instead 2FA is enabled, which may result in account loss if the auth device is lost VIDEO: - https://edufit-my.sharepoint.com/:v:/g/personal/marko_dogan_edu_fit_ba/IQCqfLcB7eCvSpsrEqnVbWYJAdJkngotPbKBR2JC3c11oCg?nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJPbmVEcml2ZUZvckJ1c2luZXNzIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXciLCJyZWZlcnJhbFZpZXciOiJNeUZpbGVzTGlua0NvcHkifX0&e=7kzlTx | Executing/Controlling | Post-Deployment | High | Letterboxd Development Team | 2026-01-05 | 8hr | New | Not resolved – defect logged | [6 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).